## Obligated funds
DRY GRAIN PULSES CRSP
STATEMENT OF FUNDS RECEIVED FROM USAID AND OBLIGATIONS TO SUBCONTRACTORS
OCTOBER 1, 2007 - SEPTEMBER 30, 2009
Obligation of funds from USAID to MSU
| Obligated Funds from USAID to MSU | Date | Amount
| Subagreement | 2007-10-01 | 3008720
| Modification 1 | 2008-09-03 | 2005000
| Total |  | 5013720
Obligation of funds to subcontractors by MSU
| FY 08 Obligations plus IDC | FY 09 Obligations | FY 08 & 09 Capacity Building Funds
| 04/01/08-09/30/08 | 10/01/08-09/30/09 | 04/01/08-09/30/09
*MANAGEMENT OFFICE (10/01/07) | 575237 | 399545 | 0
CORNELL UNIVERSITY | 94901 | 169220 | 29100
PENNSYLVANIA STATE UNIVERSITY | 109355 | 189476 | 0
MICHIGAN STATE UNIVERSITY- BERNSTEN | 91831 | 156093 | 0
UNIVERSITY OF PUERTO RICO | 100000 | 178250 | 55000
UNIVERSITY OF CALIFORNIA - RIVERSIDE | 108115 | 166706 | 74600
MICHIGAN STATE UNIVERSITY- KELLY | 78756 | 160971 | 29500
UNIVERSITY OF ILLINOIS | 86775 | 165602 | 40238
IOWA STATE UNIVERSITY | 142967 | 183063 | 47182
Total | 1387937 | 1768926 | 275620
* Management Office first day of operation was October 1, 2007
| Total obligations from USAID |  | 5013720
| Obligated funds to subcontractors |  | 3432483
| Available unobligated funds (Forward Funding) |  | 1581237
| FY 08 Obligations plus IDC | FY 09 Obligations | FY 08 & 09 Capacity Building Funds | TOTAL
| 04/01/08-09/30/08 | 10/01/08-09/30/09 | 04/01/08-09/30/09
CORNELL UNIVERSITY | 94901 | 169220 | 29100 | 293221
PENNSYLVANIA STATE UNIVERSITY | 109355 | 189476 | 0 | 298831
MICHIGAN STATE UNIVERSITY- BERNSTEN | 91831 | 156093 | 0 | 247924
UNIVERSITY OF PUERTO RICO | 100000 | 178250 | 55000 | 333250
UNIVERSITY OF CALIFORNIA - RIVERSIDE | 108115 | 166706 | 74600 | 349421
MICHIGAN STATE UNIVERSITY- KELLY | 78756 | 160971 | 29500 | 269227
UNIVERSITY OF ILLINOIS | 86775 | 165602 | 40238 | 292615
IOWA STATE UNIVERSITY | 142967 | 183063 | 47182 | 373212
Total | 812700 | 1369381 | 275620 | 2457701

## Managment Office
DRY GRAIN PULSES CRSP
COMPARISON OF MANAGEMENT OFFICE BUDGET TO EXPENDITURES
OCTOBER 1, 2007 - FEBRUARY 28, 2009
Description | Budget 10/1/07-9/30/08 | Budget 10/1/08-9/30/09 | Expenses as of 02/28/09 | Balance
Salary | 198340 | 199932 | 248228.12 | 150043.88
Fringe benefits | 65608 | 68020 | 82842.86 | 50785.14
Travel (Includes Global PI Meeting in Barcelona & TMAC Meetings) | 157214 | 23144 | 134614.81 | 45743.19
Contractual Services | 11375 | 0 | 8179.5 | 3195.5
Supplies & Materials | 24000 | 26004 | 11256.14 | 38747.86
Indirect Cost | 118700 | 82445 | 126131.57 | 75013.43
Total | 575237 | 399545 | 611253 | 363529
| Description | Budget10/1/07-9/30/09 | Expenses 10/1/07-2/28/09 | Balance
| Salary | 398272 | 248228.12 | 150043.88
| Fringe benefits | 133628 | 82842.86 | 50785.14
| Travel (Includes Global PI Meeting in Barcelona & TMAC Meetings) | 180358 | 134614.81 | 45743.19
| Contractual Services | 11375 | 8179.5 | 3195.5
| Supplies & Materials | 50004 | 11256.14 | 38747.86
| Indirect Cost | 201145 | 126131.57 | 75013.43

## BUDGET V EXPENSE
DRY GRAIN PULSES CRSP
COMPARISON OF PROJECTS BUDGET TO EXPENDITURES
APRIL 1, 2008 - FEBRUARY 28, 2009
| BUDGET 4/1/08 - 9/30/09 | U.S INST. EXP. 4/1/08-2/28/09 | HC EXP 4/1/08 - 2/28/09 | BALANCE | % REPORTED SPENT | % TO BE SPENT
CORNELL UNIVERSITY | 293221 | 58050 | 88768 | 146403 | 50.07% | 49.93%
PENN STATE | 298831 | 30547 | 46997 | 221287 | 25.95% | 74.05%
MSU- BERNSTEN | 247924 | 36901 | 85189 | 125834 | 49.24% | 50.76%
UNIV. PUERTO RICO | 333250 | 25195 | 177627 | 130428 | 60.86% | 39.14%
UNIV. CALIFORNIA | 349420 | 18003 | 70337 | 261080 | 25.28% | 74.72%
MSU- KELLY | 269227 | 109106 | 84833 | 75288 | 72.04% | 27.96%
UNIVERSITY OF ILLINOIS | 292616 | 61464 | 67589 | 163563 | 44.1% | 55.9%
IOWA STATE UNIVERSITY | 373212 | 22886 | 163797 | 186529 | 50.02% | 49.98%

## COST SHARE
DRY GRAIN PULSES CRSP
COMPARISON OF REQUIRED TO REPORTED COST SHARE
APRIL 1, 2008 - FEBRUARY 28, 2009
| REQUIRED COST SHARE 4/1/08-9/30/09 | REPORTED COST SHARE 4/1/08-2/28/09 | BALANCE
*MANAGEMENT OFFICE | 243696 | 149244 | 94452
CORNELL UNIVERSITY | 42757 | 19732 | 23025
PENN STATE | 114000 | 33434 | 80566
MSU- BERNSTEN | 36280 | 12532 | 23748
UNIV. PUERTO RICO | 61030 | 1456 | 59574
UNIV. CALIFORNIA | 37081 | 9630 | 27451
MSU- KELLY | 66250 | 39709 | 26541
UNIVERSITY OF ILLINOIS | 113854 | 8688 | 105166
IOWA STATE UNIVERSITY | 77927 | 17332 | 60595
* Management Office Cost Share is from October 1, 2007 through February 28, 2009
| Required 10/1/07- 9/30/09 | Reported 10/1/07-02/28/09 | Balance
Program Cost Share | 573828 | 291757 | 282071

## Dir V INDIRECT EXPENSES
DRY GRAIN PULSES CRSP
COMPARISON OF PROJECT DIRECT & INDIRECT EXPENSES
APRIL 1, 2008 - FEBRUARY 28, 2009
| DIRECT EXPENSES 4/1/08-2/28/09 | INDIRECT EXPENSE 4/1/08 -2/28/09 | % DIRECT | % INDIRECT
*MANAGEMENT OFFICE | 485121 | 126132 | 79.37% | 20.63%
CORNELL UNIVERSITY | 117778 | 29041 | 80.22% | 19.78%
PENN STATE | 55035 | 22509 | 70.97% | 29.03%
MSU- BERNSTEN | 91284 | 30806 | 74.77% | 25.23%
UNIV. PUERTO RICO | 176531 | 26291 | 87.04% | 12.96%
UNIV. CALIFORNIA | 71952 | 16388 | 81.45% | 18.55%
MSU- KELLY | 144044 | 49895 | 74.27% | 25.73%
UNIVERSITY OF ILLINOIS | 83260 | 45793 | 64.52% | 35.48%
IOWA STATE UNIVERSITY | 156864 | 29819 | 84.03% | 15.97%
* Management Office expenses are from October 1, 2007 through February 28, 2009

## Capacity Building
DRY GRAIN PULSES CRSP
SUMMARY of Recommendations by TMAC (August 27, 2008)
Proposals to Enhance HC Institutional Capacity Building (FY 2009)
Proposal Overview
Proposal # | Beneficiary Host Country Institution | Proposed Activity | Total Budget Requested | Amount of funding approved | Comments
1 | Kenya Agriculture Research Institute(KARI) | Strengthening communications b/t Nat'l Institution & Cornell Univ., Training for lab services, Foster Closer Collaboration b/t KARI & Univs., Capacity building through farmer-research-student exchange, Conference participation. | 52592 | 29100 | Fully fund Activities 1 (Strengthening Communications) and 2 (Training of lab services), partial support for Activity 3 (training of two M.Sc. Students plus travel expenses for two supervisors but no supervisor allowances, 50% funding for Activity 4 (Exchange Visits) and no funding for Activity 5 (Conferences) | Cornell
2 | Kigali Institute of Science & Technology (KIST), Rwanda | Product development & shelf stability, purchase rapid nutrient analyzer to facilitate direct comparisons b/t KIST & Makerere Univ. | 28182 | 28182 | Fund the budget as requested | Iowa State
3 | Makerere University, Uganda | Purchase rapid nutrient analyzer & lab scale extruder, contribute to capacity building for KIST in Rwanda via co-supervision of KIST student & coordination of KIST activities in Uganda | 55946 | 19000 | Fund all the activities except the line items for Coordinator and Pilot Scale Extruder | Iowa State
4 | Institut des Sciences Agronomiques du Rwanda (ISAR) | Organize visit of Louis Butare (bean breeder at ISAR) to Ecuador to interact w/bean breeders in INIAP with visits to bush bean and climbing bean production sites | 2000 | 2000 | Fund the budget as requested | Ecuador
5 | Institut des Sciences Agronomiques du Rwanda (ISAR) | Purchase a truck to facilitate substantial in-country movements to conduct reseach, surveys, trainings & trials | 27500 | 27500 | Fund the budget as requested | MSU (Kelly)
6 | Instituto de Investigacão Agronómica (IIA), Angola | Purchase equipment & a vehicle for IIA research station at Huambo | 57910 | 33600 | Only Fund: Vehicle, one balanca de precisao, and pH meter | UCR
7 | Institut de l'environnment et de recherches Agricoles (INERA), Burkina Faso | Repair vehicle for field research, equip weather station at Pobe Mengao, scientific-training visit to Senegal | 11000 | 11000 | Fund the budget as requested | UCR
8 | ISRA, Senegal | Purchase vehicle to facilitate research | 30000 | 30000 | Fund the budget as requested | UCR
9 | l'Institut National de la Recherche Agronomique du Niger, Institut de l'Environment et des Recherches Agricole, Institute for Ag. Research, Institut d'Economie Rurale, International Institute of Tropical Ag. (West Africa) | Training of biological control techniques and development of strategies to control Maruca vitrata, promote Neem-based control strategies of cowpea pests in Mali | 64738 | 40238 | Only fund: biological control training activity (budget for IITA) and Farmer Field School activity (budget for IER) | UIUC
10 | Instituto de Investigacão Agronómica (IIA), Angola | Repair greenhouse facilities & purchase equipment for IIA research station at Huambo | 40850 | 25000 | Only fund: Greenhouse repairs, autoclave with accessories, and $6000 for microscope with camera | UPR
11 | Escuela Agrícola Panamericano (Zamorano), Honduras | One-week workshop to include review plant-breeding, field research and lab procedures | 26275 | 30000 | Fund as requested plus an additional $ 3,725 to include cowpea component in the training workshop | UPR
|  | Total | 396993 | 275620 | Total approved funding
|  | Difference |  | -24380 | Discretionary funds for MO

## MO
DRY GRAIN PULSES CRSP
COMPARISON OF MANAGEMENT OFFICE BUDGETED EXPENSES TO ACTUAL EXPENSES
OCTOBER 1, 2007 - FEBRUARY 28, 2009
| Date | Budgeted Expenses | Actual Expenses
| 10/1/07-12/31/07 | 121847.75 | 67848.79
| 1/1/08-3/31/08 | 243695.5 | 259530.38
| 4/1/08-6/30/08 | 365543.25 | 383899.99
| 7/1/08-9/30/08 | 487391 | 468111.09
| 10/1/08-12/31/08 | 609238.75 | 553624.43
| 1/1/09-3/31/09 | 731086.5 | 611253
| 4/1/09-6/30/09 | 852934.25
| 7/1/09-9/30/09 | 974782

## Cornell Univ.
DRY GRAIN PULSES CRSP
COMPARISON OF PROJECTS BUDGET TO EXPENDITURES
APRIL 1, 2008 - FEBRUARY 28, 2009
| Date | Budgeted Expenses | Actual Expenses
| 4/1/08-6/30/08 | 48870 | 0
| 7/1/08-9/30/08 | 97740 | 0
| 10/1/08-12/31/08 | 146610 | 79072
| 1/1/09-3/31/09 | 195480 | 153318
| 4/1/09-6/30/09 | 244350
| 7/1/09-9/30/09 | 293220

## Penn State
DRY GRAIN PULSES CRSP
COMPARISON OF PROJECTS BUDGET TO EXPENDITURES
APRIL 1, 2008 - FEBRUARY 28, 2009
| Date | Budgeted Expenses | Actual Expenses
| 4/1/08-6/30/08 | 48722 | 0
| 7/1/08-9/30/08 | 97444 | 0
| 10/1/08-12/31/08 | 146166 | 0
| 1/1/09-3/31/09 | 194888 | 84044
| 4/1/09-6/30/09 | 243610
| 7/1/09-9/30/09 | 292332

## MSU Bernsten
DRY GRAIN PULSES CRSP
COMPARISON OF PROJECTS BUDGET TO EXPENDITURES
APRIL 1, 2008 - FEBRUARY 28, 2009
| Date | Budgeted Expenses | Actual Expenses
| 4/1/08-6/30/08 | 41745 | 53822
| 7/1/08-9/30/08 | 83490 | 62250
| 10/1/08-12/31/08 | 125235 | 85267
| 1/1/09-3/31/09 | 166980 | 122091
| 4/1/09-6/30/09 | 208725
| 7/1/09-9/30/09 | 250470

## UPR
DRY GRAIN PULSES CRSP
COMPARISON OF PROJECTS BUDGET TO EXPENDITURES
APRIL 1, 2008 - FEBRUARY 28, 2009
| Date | Budgeted Expenses | Actual Expenses
| 4/1/08-6/30/08 | 55542 | 77830
| 7/1/08-9/30/08 | 111084 | 77830
| 10/1/08-12/31/08 | 166626 | 137246
| 1/1/09-3/31/09 | 222168 | 202822
| 4/1/09-6/30/09 | 277710
| 7/1/09-9/30/09 | 333252

## UCR
DRY GRAIN PULSES CRSP
COMPARISON OF PROJECTS BUDGET TO EXPENDITURES
APRIL 1, 2008 - FEBRUARY 28, 2009
| Date | Budgeted Expenses | Actual Expenses
| 4/1/08-6/30/08 | 58237 | 0
| 7/1/08-9/30/08 | 116474 | 0
| 10/1/08-12/31/08 | 174711 | 0
| 1/1/09-3/31/09 | 232948 | 94840
| 4/1/09-6/30/09 | 291185
| 7/1/09-9/30/09 | 349422

## MSU Kelly
DRY GRAIN PULSES CRSP
COMPARISON OF PROJECTS BUDGET TO EXPENDITURES
APRIL 1, 2008 - FEBRUARY 28, 2009
| Date | Budgeted Expenses | Actual Expenses
| 4/1/08-6/30/08 | 44872 | 54929
| 7/1/08-9/30/08 | 89744 | 74199
| 10/1/08-12/31/08 | 134616 | 150624
| 1/1/09-3/31/09 | 179488 | 182820
| 4/1/09-6/30/09 | 224360
| 7/1/09-9/30/09 | 269232

## UIUC
DRY GRAIN PULSES CRSP
COMPARISON OF PROJECTS BUDGET TO EXPENDITURES
APRIL 1, 2008 - FEBRUARY 28, 2009
| Date | Budgeted Expenses | Actual Expenses
| 4/1/08-6/30/08 | 48770 | 0
| 7/1/08-9/30/08 | 97540 | 0
| 10/1/08-12/31/08 | 146310 | 0
| 1/1/09-3/31/09 | 195080 | 129053
| 4/1/09-6/30/09 | 243850
| 7/1/09-9/30/09 | 292620

## ISU
DRY GRAIN PULSES CRSP
COMPARISON OF PROJECTS BUDGET TO EXPENDITURES
APRIL 1, 2008 - FEBRUARY 28, 2009
| Date | Budgeted Expenses | Actual Expenses
| 4/1/08-6/30/08 | 62202 | 0
| 7/1/08-9/30/08 | 124404 | 100159
| 10/1/08-12/31/08 | 186606 | 139086
| 1/1/09-3/31/09 | 248808 | 193183
| 4/1/09-6/30/09 | 311010
| 7/1/09-9/30/09 | 373212

## Contractual Data Timeline
DRY GRAIN PULSES CRSP (October 1,2007 - September 30, 2012)
PHASE I PROJECTS
CONTRACTUAL DATA TIMELINE
U.S Institution Subcontractor | Sub Subcontractors | Cost reimbursable contract was signed | Fixed Price contract was finilized
Cornell University |  | April 6,2008
| KARI (Kenya) |  | May 15,2008
Pennsylvania State University |  | June 30,2008
| EAP (Honduras) |  | May 9,2008
| IIAM (Mozambique) |  | September 12,2008
Michigan State University (Bernsten)
| EAP (Honduras) |  | June 12,2008
| IIAM (Mozambique) |  | May 20,2008
| Universidade Agostinho Neto (Angola) |  | June 3,2008
University of Puerto Rico |  | April 21,2008
| USDA | March 2,2008
| EAP (Honduras) |  | June 12,2008
| Ministry of Agriculture (Haiti) |  | June 2,2008
| IIA (Angola) |  | May 23,2008
University of California - Riverside |  | June 28,2008
| INERA (Burkina Faso) |  | September 29,2008
| ISRA (Senegal) |  | September 12,2008
| IIA (Angola) |  | February 3,2009
Michigan State University (Kelly)
| Cornell University | April 16,2008
| INIAP (Ecuador) |  | May 22,2008
| ISAR (Rwanda) |  | May 20,2008
University of Illinois |  | May 8,2008
| INERA (Burkina Faso) |  | September 28,2008
| INRAN (Niger) |  | September 1,2008
| IAR (Nigeria) |  | September 22,2008
Iowa State Univeresity |  | April 7,2008
| KIST (Rwanda) |  | June 12,2008
| NaCRRI (Uganda) |  | June 4,2008
| MAKARERE (Uganda) |  | June 4,2008
| VEDCO (Uganda) |  | June 6,2008