## All projects
|  | STEP 1 |  | STEP 2 |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed |  |  |  |  | STEP 3
Project | Lead PI | Project Outputs (expected by FY 12) | When to be achieved? | Next Users | Final Users | Step 4.1 | Step 4.2 | Step 4.3 | Step 4.4 | Step 4.5 | Vision of Success | Expected time to achieve the vision
PII-ISU-1 | Mazur | Capacity Building Approach for Improved Crop Production & Post-Harvest Mgmt. practices and technologies | 2012-06-30 | Volunteer Efforts for Development Concerns (NGO) | Community Farmers | Finalize extension materials (soil prep., planting, production, disease & pest control, drying, and storage) | 'Publish' extension materials in print and ditigal formats | 6 farmer groups train 3 other groups in same parish, 6 groups in another parish | Quality seeds accessed through farmer groups, associations, and markets | Follow up training and support for newly trained farmer groups | At least 20% of farmers in 10 parishes in Kamuli achieve 50% higher effective yields through promoted crop prod. & post-harvest mgmt. practices and technologies | 2015
PII-ISU-1 | Mazur | Community-Based Seed Production (CBSP) Model established | 2012-06-30 | Volunteer Efforts for Development Concerns (NGO) | Community Farmers | Identification of 5 potential new secondary CBSP groups in each of 6 new parishes | 6 experienced CBSP groups each provide 1000 kg. of quality selected seeds properly stored | Each CBSP group trains and supports 5 new secondary CBSP groups in another parish | 30 new secondary CBSP sites established | Quality seeds made available through farmer groups, associations, and markets | At least 10% of farmers in 10 parishes in Kamuli are growing promoted bean varieties | 2015
PII-ISU-1 | Mazur | Capacity Building Approach for Collective Marketing of promoted bean varieties | 2012-08-31 | Volunteer Efforts for Development Concerns (NGO) | Community Farmers | Effective bean market information system established throughout district | 30 farmer groups, 20 members each, trained in business mgmt., gender & group dynamics, and collective mktg. | Strong links established btw. farmer groups / associations and food processing businesses | 60 farmer groups in 6 new parishes, trained (business mgmt., gender & group dynamics, and collective mktg.) | Follow up training and support for newly trained farmer groups and their marketing associations | At least 20% of farmers in 10 parishes in Kamuli are involved in marketing > 100 kg. of beans each | 2015
PII-ISU-1 | Mazur | New Methods of Consuming Beans (soups, porridge, extruded products, weaning foods, snacks) | 2012-08-31 | Volunteer Efforts for Development Concerns (NGO) & Food Processing Businesses | Community Farmers and Urban Consumers | Finalize extension materials for methods of bean processing (incl. cold extrusion) and cooking | Train 20 farmer groups in 4 current parishes on new methods of bean processing and cooking | Train 30 farmer groups in 6 new parishes new methods of bean processing and cooking | Work with 6 food processing businesses in develoment of marketing strategies for bean products | Obtain feedback from consumers (rural and urban) of new methods of consuming beans, adjust as appropriate | At least 15% of farmers in 10 parishes using alternative methods of preparing beans, consuming bean products, and complementary foods | 2015
PII-MSU-1 | Kelly | 50 advanced lines in two growth habits and contrasting seed types with multiple disease resistance, consumer acceptance | 2010-04-01 | Farmers-CIAL members | Farmers- bean growers in country | On station seed increases | On farm testing and selection | On farm seed multiplication of selected lines | Basic seed available | Commercial seed available of new varieties | Successful release, adoption and utilization of at least four varieties - in two growth habit and four seed types for production in Rwanda and Ecuador | 2013
PII-MSU-1 | Kelly | Increase knowledge for research scientists and stakeholders in bean production practices and constraints | 2012 | Research and outreach scientists and stakeholders | Government, Univesity, NGO Personel | Meeting with project leaders | Field days at CIALs, and on-station | Workshops, short courses | Radio, TV, internet, bulletins, and newspaper coverage | Country exchange of scientists and stakeholders
PII-MSU-2 | Bernsten | Market price information on beans and cowpeas via cellphone, as well as through other means, will be available. Working with NGOs including World Vision and ADRA in Zambezia, targeting at least 4,000 farmers by 2012. | FY12 | Extension workers and farmers in the main bean production zones in Zambezia & Tete provinces (piloted with NGOs) | Bean/cowpea farmers and traders throughout the country | SIMA system designs info system for diffusion of bean/cowpea price info via SMS | SIMA Provincial systems incorporate info in local radio broadcasts as well as with SMS text | Local SIMAP partner with NGOs for system development and dissemination | Information to IIAM breeding staff and seed companies to ensure seed availability for beans/cowpeas with known marketable characteristics | Extension agents and lead farmers are trained in using SMS and in understanding market price info | Linakges established with local radio stations to broadcast market information | Traders are linked to the system and information to link traders and producers also disseminated through the system | At least 40% of farmers in the pilot zones (defined by NGO areas of work) accessing information to ensure profitability and motivate productivity enhancements and production increases | FY2014
PII-MSU-2 | Bernsten | Market price information will be circulated through cell phones. Farmers will access new markets for beans and cowpeas. Expected population affected would be at least 20% of World Vision's 27,000 farmers in the Planalto region. | Fy2012 | Extension workers and farmers in pilot areas | Traders and farmers in the key production zones | Marketing channels identified for beans in Planalto region | Farmer bean and cowpea marketing strategies identified and opportunities vealuated for improving marketing | Marketing channels identified for cowpeas in Planalto region | New markets evaluated for beans and cowpeas in Luanda | Extension agents and lead farmers for NGO are trained in market information use | All of NGO Farmer organizations in key bean production zone are linked to new marketing channels through cellphones and NGO |  | 50% of farmer associations working with NGO are marketing beans using new channels, where more profitable; 25% using price information | 2014
PII-MSU-2 | Bernsten | A pilot bean production and marketing system for small-scale farmers oriented towards producing fair trade beans for export to a US retailer | FY 2011 | Small-scale farmers | US retailer of fair trade beans | Trial to assess organic bean production technologies | Assess costs for producing & exporting fairtrade beans | Identify a US retailer interested in purchasing fairtrade beans | Obtain third party fairtrade certification of the small-scale farmers | Finalize supply chain arrangements | Contract farmers to produce fair trade beans | Export fairtrade beans to a US retailer | Small-scale farmers produce and export fairtrade beans to th US | FY 2011
PII-PSU-1 | Lynch | validated root traits used in bean breeding programs | some deployed now, others in the pipeline | bean breeders | Farmers in bean growing region | identify traits | confirm utility of traits for bean performance in stressful soils | characterize genetic control of traits | evaluate agroecological effects of traits on bean production systems | develop rapid screen for traits | work with breeders to use screen to identify promising sources and to assist introgression or recurrent selection for traits | Multiple varieties (5+) low-P bean seed available in local markets/ through seed-sharing networks. Bean income higher; local food supply more secure. | impacts are already being observed- extension of impacts dependent on adoption of bnoew bean seed by farmers- the subject of Dr. Findeis' activities
PII-PSU-1 | Lynch | SES assessment, policy studies | 2012 - first wave | IIAM field staff | Farmers in bean growing region, policy makers | Conduct ex ante impact assessment at SES experimental sites | Participatory Variety Selection at SES experimental sites | Test selected seed with randomly- selected farm households | Work with NGOs, comm. seed producers and extension to improve low-P seed distribution | Conduct ex post impact assessment at SES experimental sites | Provide policy makers with knowledge of documented impacts and constraints to low-P seed diffusion | Multiple varieties (5+) low-P bean seed available in local markets/ through seed-sharing networks. Bean income higher; local food supply more secure. Policy makers taking steps to improve bean seed system in Mozambique/region. | 1) 2012 - local impacts observaable in growing region; 2) 2015 - changes in national/national policy to reduce potential constraints to low-P seed diffusion
PII-UCR-1 | Roberts | Senegal advanced lines with large white grain and medium- to late maturity generated and available | 2012-09-01 | ISRA Seed Unit, Certified Seed Producers (NGOs, cops | Farmers | Multi-locational testing to validate results | Breeder seed production | Foundation seed | Production of 60 T of Certified (commercial) seed | Commercial seeds distributed available in market | At least 10% of farmers in the northern agro-ecological production zone in Senegal are growing the released variety | 2013
PII-UCR-1 | Roberts | Burkina Faso advanced lines with Striga resistance and improved grain quality (white) generated and available | 2010-09-12 | INERA Seed Unit, Certified Seed Producers (NGOs, cops | Farmers | Multi-locational testing to validate results | Breeder seed production | Foundation seed | Production of 60 T of Certified (commercial) seed | Commercial seeds distributed available in market | At least 10% of farmers in the central and northern agro-ecological zones in Burkina Faso are growing the released varieties | 2013
PII-UCR-1 | Roberts | Extension of CRSP cowpea varieties from Burkina Faso and Senegal into Mali and Niger | 2010-09-12 | Mali and Niger NARS Seed Systems | Farmers in Mali and Niger | Multi-locational testing to validate results | Foundation seed | Foundation and Certified seed | Production of 30 T of Certified (commercial) seed | Commercial seeds distributed available in market | At least 5% of farmers in south-west Mali and western Niger are growing one of the released varieties (see note below) | 2014
PII-UIUC-1 | Pittendrigh | Pest control strategies for cowpea farmers and scaleable extension materials targeted for extension agents, NGOs, farmer organizations, and ultimately for cowpea farmers. | 2012-09-30 | NARS, IITA, over 100 extension agents in each of the host countries, 10 NGOs per country, and 100 Farmer groups per country | minimum of 1000 cowpea farmers per country. We will target to impact over 10,000 farmers in Niger and Burkina Faso either directly or indirectly through our extension materials. | Understand pest populations in host countries (using entomological and genomic tools). We will used both biology experiments in the field coupled with molecular markers to determine basic information about timing of major pests of cowpea and potential movement patterns). This data will be summarized in an online tracking system for future groups to add to this dataset for IPM management decisions both within the context of the project and beyond the current scope of the project. This will be completed by the end of the project in 2012. | Identify practical pest control strategies for given regions: (1) Insect-based biocontrol agents (a minimum of 2 released), (2) viral sprays, (3) host plant resistant strains, (4) cultural control practices (timing of plants and plant varieties that can escape insect attack), and (5) use of local plant products in spraying of crops to control pest insects (e.g., neem extracts). | Make available materials for pest control strategies: (1) Insect-based Biocontrol agents (a minimum of 2 bio-control agents will be released in Niger, Burkina Faso, and Benin), (2) viral sprays (one viral spray against Maruca will be tested in Benin, Burkina Faso, and Niger), (3) host plant resistant strains (a minimum of one strain will be released in Mali, Niger, Burkina Faso, and Nigeria), (4) cultural control practices (timing of plants and plant varieties that can escape insect attack -- this strategy will be promoted in Niger and Burkina Faso), and (5) use of local plant products in spraying of crops to control pest insects (e.g., neem extracts)(this strategy will be promoted in Niger, Burkina Faso, and Mali -- we expect that over 1000 farmers per country will be exposed to training material on this topic). These control strategies will be made available to a miniumum of over 100 extension agents in each of the host countries, 10 NGOs per country, and 100 Farmer groups per country. We expect to impact a minimum of 1000 farmers in each country and upwarrds of potentially 10,000 famers impated in NIger and Burkina Faso. | Identify partner organizations for large scale deployment of extension strategies: NARS programs (4 programs), local universities(>5 universities), NGOs (an average of 10 per country), and international instituations (IITA). We will take two approaches to this aspect of the project. The first will involve working with partner institutions directly in West Africa. The second will involve using e-mail as a strategy to contact NGOs and potential partner organizations where we can simply e-mail them cell phone videos that can be used for extension efforts in countries where cowpeas are grown and they have contact with cowpea farmers. We will also identify and work with partner organizations (a minimum of 5 organizations in West Africa) to build an online extension system that can be used beyond the scope of this project to continually deploy extension materials). | Deployment of pest control strategies. Biocontrol agents will primarily be deploed through IITA, INERA, and INRAN. We expect the biocontrol agents to establish in the field int he region where they have been deployed. We expect that by the end of the project, these biocontrol agents should have established in the fields and will reduce attack of their target species on cowpea by 50-70%. We will record for the population levels of these pest insects before and after release of the bio-control agents. We will also document reduced insect attack due to other control practices, including virally based control strategies, host plant resistant traits, and cultural practices. We will also use all our nextworks as described in Step 4.4 to deploy the extension materials we have developed associated with many of these above issues. The extension materials will include (1) a video on biocontrol agents, (2) animations on hermetic storage of cowpea, solar treating of cowpea, and neem spraying to control pests in the field. These animations will be deployed through cell phones and the voice overs will be translated into a minimum of six languages. Depending on the availability of resources we will create other animations dealing with pest control strategies for cowpea pests (hor plant resistance, cultural practices, and viral sprays), which can also be deployed through e-mail and ultimately onto cell phones. | Regional for ultimate large-scale use in host countries of pest control strategies. We will have a diversity of pest control strategies available to farmers for the control of insects that attack cowpeas. This will have been deployed by (1) the release of biocontrol agents, virally based sprays, neem based sprays, and host plant resistant trait, (2) use of farmer field schools and training sessions through NGO and farmer groups, and (3) through the deployment of cell phone animations/videos to explain well-established pest control strategies. The biocontrol agents will be released in Benin, Burkina Faso, and Niger. Additional potential releases may occur in Nigeria and Mali. In Burkina Faso, Mali, Nigeria, and Niger we expect in excess of 10,000 farmers will be exposed to the videos with changes in agricultural practices excess of 10,000 hectares. For the biocontrol agents we expect that in the piolot deployment regions we will be able to observe 20-30% increases in production due to decreased insect attack. We expect a total of over 10,000 hectares (across all countries) should have at least one biocontrol agent established in these areas. The envisioned output that will demonstrate that this project can be scaled up to do country-wide coverage of all of these strategies. | 2012
PII-UIUC-1 | Pittendrigh | Development of extension materials and online extension sharing system that will be targeted at NARS scientists, extension agents, NGOs and farmer groups in order to increase the impact that these groups can have on deploying information into the hands of farmers. | 2012-09-30 | NARS, IITA, Extension Agents, NGOs, Farmer groups | Cowpea Farmers | Development of extension materials for low literate learners: these include a series of MP3 audio files, videos that can be played on cell phones (e.g., triple bagging, solar treating of cowpeas, neem spraying, and where time and resources permit other videso including safer ways to use traditional pesticides), posters, and booklets. | Development of online sharing system for extension materials. This is a system that will help us organize and freely share all the materials we have developed both for our project. This will allow us to organize materials in various languages and deployment strategies. We expect to have over 50 documents (which will include language variants) on this system by the end of 2011. | Testing of extension materials and feedback for improvements. This will occur through interactions between UIUC, host country scientists, and target organizations. Extension materials will be adapated or improved based on feeedback from these in country groups. | Identify partner organizations for large scale deployment of extension materials. These organizations will also be informed of our extension sharing system and the contents of this system for their own use. | Deployment of extension materials. This will be accomplished through a diversity of mechanisms as follows. Materials (CRSP created documents, animations, and videos) will be provided to NGOs and extension agenet for deployment. A total of 10 farmer field schools per country will have occurred in Niger, Burkina Faso, Nigeria, and Mali. Animations (a minimum of three different animations) will also be deployed through cell phones and Bluetooth technology through a minimum of 10 NGOs, 100 extension agents, local businesses supporting certain control strategies (e.g., triple bag manufacturers and distributors), and by e-mail to a minimum of 100 logical contact people per country. We will also have an online system supporting the exchange of extension materials. This system will allow us to track downloads of the materials. All organization will also be made aware and in some cases (NARS scientists, 20 technicians, extension agents and NGO) trained to use our online extension system. | Large scale use in host countries of extension materials for training farmers in pest control strategies. We expect that the cell phone animations will be easily transmitted through Bluetooth technology between extension agents and farmers. We also expect that our online extension sharing system will provide a useful base for a minimum of 500 cowpea educators (NARS scientists, technicians, extension educators, and NGOs) to access and share the extension materials we and others have developed. The videos will be released in Benin, Mali, Burkina Faso, Nigeria, and Niger. We expect in excess of 10,000 farmers will be exposed to the videos with changes in agricultural practices excess of 10,000 hectares. | 2012
PII-UIUC-1 | Pittendrigh | Cross training of 5 NARS scientists (P.I.'s and co-P.I.'s), 20 technicians, and 10 NGOs/farmer organizations in traditional and electronic based extension programs | 2012-09-30 | 4 NARS programs, IITA, 100 extension agents, 10 NGOs, 100 farmer groups per country | A minimum of 1000 cowpea farmers impacted per country | Training of two host country scientist in development of extension materials and provide them with the necessary tools to continue to make and adapt many of these extension materials. | Cross training activities between host country scientists (6 scientists) and technicians (a minimum of 20 technicians). This will involve meetings bringing together most or all of the host country scientists [the first meeting occurred at the beginning of the project, several smaller meetings/workshops have already occurred (e.g., Niger in the summer of 2009) and one during the 2010 World Cowpea Congress]. A minimum of 20 technicians will be trained in various in country and between country cross-training activities (including within country workshops). On average we will interact with 10 NGOs per country to provide them with extension materials for deployment through their organizations. This will help to establish a network of people that can be called upon to deliver extension materials both within the project and beyond the scope of the current project. | Concepts and materials for low literate learners in the hands of farmers (a minimum of 1000 farmers per country). This will occur through farmer field schools, workshops, NGOs, farmer organization, and other conference/outreach activities. These end result outreach efforts will be based on materials and knowledge gained in steps 4.1 and 4.2. Contact information for all of these groups will be assembled such that future extension materials that are deployed can be easily distributed through these groups. |  |  | Development of a network of scientists, technicians, NGOs, and farmer organzations where extension materials can easily and continously be delivered beyond the scope of the current project. We expect to have 4 NARs and ITTA, as well as 100 extension agents and 10 NGOs/Farmer groups per country as part of this network for current and future deployment of extension materials. | 2012
PII-UPR-1 | Beaver | Development, release and dissemination of improved bean cultivars for Central America, the Caribbean and Angola. | Sep-2012 | NARS breeders | Farm families | Selection and evaluation of bean breeding lines | Production of breeder seed by NARS | Production of foundation seed stocks by NARS, farmer associations and seed companies | Dissemination of foundation seed to bean producers |  | A significant number of farmers (100,000) in Central America and Haiti adopt improved bean varieties resulting in increased or more stable yields. Bean lines are identified as candidates for release in Angola. | September 2013
PII-UPR-1 | Beaver | Selection of beans for adaptation to low N soils. | Sept 2013 | NARS breeders | Farm families | Selection and evaluation of bean breeding lines | Multi-locational testing conducted in Central America, Haiti and Angola | Release of improved bean germplasm and use as a parent by NARS breeding programs |  |  | Parental lines that can be used by NARS bean breeding programs to improve adaptation to low soil fertility | September 2013
PII-UPR-1 | Beaver | Develop and test molecular markers for disease and pest resistance. | Sept 2013 |  |  | Develop molecular markers for disease and pest resistance. | Test molecular markers to select for disease and pest resistance. |  |  |  | Molecular markers that can be used by NARS bean breeding programs to select bean lines with enhanced levels of disease and pest resistance | September 2013
PII-UPR-1 | Beaver | Increase the capacity, effectiveness and sustainability of agriculture research institutions that serve the bean and cowpea sectors in Central America, Haiti and Angola. | Sept 2013 | NARS bean programs | NARS bean programs | Formal (M.S. degree) and informal training (workshop) activities |  |  |  |  | Trainees utilize knowledge to conduct new techniques or realize bean research activities with greater efficiency or effectiveness | Sept 2013
PIII-ISU-2 | Westgate | Quantitative relationships between local environmental conditions and genetic response to inoculants established | 2012-09-28 | Research stations and selected farmers | Small landholder Farmers | Identify local varieties and demonstration sites for field testing | Complete initial assessment of G x E, refine variety list | Confirm Trial I resuts, initiate on-farm trials | Test selected/advanced germplasm in zones with defined ecological limitations | Identify unique responses/limitations for improving seed yield across agro-ecological zones | Identify consistent response/limitations for improving seed yield across agro-ecological zones | Test optimum combinations of germplasm and inoculant for each ecological zone | Confirm optimum combinations of germplasm, inoculant, soil management for small - farm profitability | Best combinations of varieity and inoculants determined for 9 agro-ecological zones in Uganda, Rwanda, Tanzania | 2015
PIII-ISU-2 | Westgate | Germplasm (for parental materials) with enhanced BNF identified | 2012-09-28 | Researchers | Breeders, IARCS | Select germplasm for evaluation with high and low BNF | Screen for BNF response to inoculants in US and HC | Test for BFN response to specific stresses | Advance positive response lines to field testing in US and HC. | Correlate reponse to inoculation in GH and field trials | Confirm G x E response for selected germplasm | Link G X E response to nodule occupancy/ efficiency | Relate BNF levels to rhizobia strains occupying nodules | Germplasm with superior nodulation characteristics identified and made available to breeding programs to improve BNF | 2012
PIII-ISU-2 | Westgate | Iinitial set of new QTLs for response to inoculation identified | 2012-09-28 | Researchers | Breeders, IARCS | Secure mapping populations for analysis | Establish field trials for phenotypic analysis | Correlate BFN response under field and controlled conditions | Advance RILs for SSR marker analysis | Conduct SSR marker analysis on selected lines | Complete initial analysis of potential new QTLs | Advance selected RILs to F3 for QTL analysis | Test selected RILs in agro-ecological zones to confirm QTLs for response to inoculation | QTLs for response to inoculation confirmed and employed in breeding programs to improve BNF | 2015
PIII-ISU-2 | Westgate | knowledge and recommendations generated from Inoculation trial results | 2012-09-28 | farmers | ag business concerns | Add inoculation information to PELUM agenda | Create appropriate information format for dissemination | Meet with key farmer groups in each HC | Share project results through PELUM network in HCs | Engage external funding agencies through HC ag stakeholders | Develop locally-relevant information materials for dissemination to PELUM network farmers | Develop extension training and farmer advocacy programs to promote access to inoculant technologies | Conduct PELUM meetings in all network countries | Fifteen (15) percent of farmers in all 12 SSA countries in PELUM network using innoculum technology | 2014
PIII-ISU-2 | Westgate | Students, staff, farmers trained on ways to utilize, manage, and improve BNF | 2012-09-28 | staff, farmers | graduate students | identify beneficiaries | Identify beneficiaries of training programs | Train farmers and staff for research station and on-farm trials | Initiate graduate student research projects | Complete graduate student research projects | Develop scientific publications from graduate theses research | Graduate degrees awarded |  | All degree programs, internships, and visiting scientist activities successfully completed | 2012
PIII-MSU-3 | Bennink | Reduced inflammation | 2012 | other scientists and health advocates | individuals, food processors and retailers | Additional research related to pulse consumption and reduction in markers of chronic disease | consumer and commodity advocates instigate change in nutritional recommendations by national and international agencies | recommendations are implemented at grassroots | Changes in food choices | improved health and reduction in health costs | Reduction in chronic diseases | 2045
PIII-MSU-3 | Bennink | Improved nutritional and immunological status | 2012 | other scientists and health advocates | individuals, food processors and retailers | Funding agencies are convinced to provide funds for large scale multi-national testing of nutritional intervention for PLHA | Decision makers are convinced that nutritional support is important enough to provide resources | policy change and commitment of resources for nutritional support and not just for drugs | changes in food choices and increased consumption of pulses and essential nutrients | improved health and reduction in health costs | Improved quality of life and decreased medical costs for people living with HIV and AIDS
PIII-TAMU-1 | Awika | Identity and health promoting properties of cowpea bioactives | 2012-10-01 | Scientific community, nutritionists, Food scientists, NGOS, Policymakers | Farmers, nutritionists, Food manufacturers, Consumers | Establish effect of food processing on cowpea bioactives | Effect of feeding cowpea products on biomarkers in animal models | Short term human feeding trials | Long term human feeding trials | Community outreach targeting consumers, policymakers and farmers | 50% Increase in demand and use of cowpeas with enhanced health benefits in foods in HC; Improved health and food security among vulnerable groups; 30% Improvement in income for cowpea farmers | 2022
PIII-TAMU-1 | Awika | Identity of healthy cowpea lines and and heritability of health promoting traits in cowpea | 2012-10-01 | HC breeders, Food Scientists, Nutritionists, Policymakers, scientific community | Seed companies, Farmers, Breeders, Policymakers, Food manufacturers | Infuse bioactivity traits in cowpea lines with suitable agronomic properties | Field adaptability trials across different environmets | Development of suitable local varieties by HC breeders and seed companies | Farmer training and field demonstrations | Community outreach targeting policymakers and farmers | Development of at least 2 local varieties with high phytochemical content and enhanced health benefits in each HC | 2017
PIII-KSU-1 | Vincent | Information and knowledge about the structure, conduct and performance in bean and cowpea supply chains in Zambia | 2012 | Producers and their downstream partners | Policy makers and producers and their downstream partners | Establish baseline knowledge about structure, conduct and performance in the bean and cowpea supply chains through primary data collection and analysis | Explore effect of current institutional structures and policies on baseline conditions through engaged conversations and simulations with policymakers | Develop and test alternative governance systems that minimize policy impacts and enhance participation | Use information from tests to improve governance system alternatives and develop |  | Effective participation by the majority of producers in bean and cowpea supply chains as a result of improved understanding of value chain operations, leading to higher value accretion and resulting in improved household food and nutrition security. Realisitic quantitative metrics will be supplied after preliminary field work is completed in Feb. 2011. | 2015
PIII-KSU-1 | Amanor-Boadu |  |  |  |  | Establish baseline knowledge about structure, conduct and performance in the bean and cowpea supply chains through primary data collection and analysis | Explore effect of current institutional structures and policies on baseline conditions through engaged conversations and simulations with policymakers
[8 empty] | Develop and test alternative governance systems that minimize policy impacts and enhance participation | Use information from tests to improve governance system alternatives and develop
PIII-KSU-1 | Amanor-Boadu | Development of adoption protocols to enhance the relationship between value accretion and gender | 2011 | Producers | Producers and policy makers | Establish current participation and value accretion situation by gender | Engage female producers to explicitly explore challenges and opportunities for effective participation in supply chains | Explore opportunities to implement ideas emanating from the engagements with female producers | Discuss simulation results with producers and develop clear feasible implementation and/or adoption protocols | Engage government and other organizations to implement ideas that prove promising after simulations and testing | Enhanced income accruing to female producers through effective engagement in their supply chains. Realisitic quantitative metrics will be supplied after preliminary field work is completed in Feb. 2011 | 2015
Establish current participation and value accretion situation by gender
[7 empty] | Engage female producers to explicitly explore challenges and opportunities for effective participation in supply chains | Explore opportunities to implement ideas emanating from the engagements with female producers and simulate ideas for effects on expected outcome | Discuss simulation results with producers and develop clear feasible implementation and/or adoption protocols | Engage government and other organizations to help implement ideas that prove promising after simulations and testing

## PII-ISU-1
Impact Pathway Worksheet (Feel free to expand rows and columns as needed). Don't enter any thing in gray cells.
Name of your CRSP Project (Shorter version): |  |  |  |  | Enhancing Nutritional Value and Marketability of Beans in Uganda and Rwanda
|  |  |  | Lead PI: | MAZUR
|  |  | STEP 1 |  | STEP 2 |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed |  |  |  |  | STEP 3
ID# |  |  | Project Outputs (expected by FY 12) | When to be achieved? | Next Users | Final Users | Step 4.1 | Step 4.2 | Step 4.3 | Step 4.4 | Step 4.5 | Vision of Success | Expected time to achieve the vision
1 | Vision of Impact pathway |  | Capacity Building Approach for Improved Crop Production & Post-Harvest Mgmt. practices and technologies | 2012-06-30 | Volunteer Efforts for Development Concerns (NGO) | Community Farmers | Finalize extension materials (soil prep., planting, production, disease & pest control, drying, and storage) | 'Publish' extension materials in print and ditigal formats | 6 farmer groups train 3 other groups in same parish, 6 groups in another parish | Quality seeds accessed through farmer groups, associations, and markets | Follow up training and support for newly trained farmer groups | At least 20% of farmers in 10 parishes in Kamuli achieve 50% higher effective yields through promoted crop prod. & post-harvest mgmt. practices and technologies | 2015
| STEP 5 | FY 10 |  |  |  |  | Provision of logistical support
|  | FY 11 |  |  |  |  | Pre-test materials |  | Identification of new groups | Multiplication of local and foundation seed
|  | FY 12 | [8 empty] | Tracking changes from training
2 | Vision of Impact pathway |  | Community-Based Seed Production (CBSP) Model established | 2012-06-30 | Volunteer Efforts for Development Concerns (NGO) | Community Farmers | Identification of 5 potential new secondary CBSP groups in each of 6 new parishes | 6 experienced CBSP groups each provide 1000 kg. of quality selected seeds properly stored | Each CBSP group trains and supports 5 new secondary CBSP groups in another parish | 30 new secondary CBSP sites established | Quality seeds made available through farmer groups, associations, and markets | At least 10% of farmers in 10 parishes in Kamuli are growing promoted bean varieties | 2015
| STEP 5 | FY 10
|  | FY 11 |  |  |  |  | Provision of inputs to produce seed | Monitoring of activities |  |  | Harvest, dry, clean and store best seed
FY 12
3 | Vision of Impact pathway |  | Capacity Building Approach for Collective Marketing of promoted bean varieties | 2012-08-31 | Volunteer Efforts for Development Concerns (NGO) | Community Farmers | Effective bean market information system established throughout district | 30 farmer groups, 20 members each, trained in business mgmt., gender & group dynamics, and collective mktg. | Strong links established btw. farmer groups / associations and food processing businesses | 60 farmer groups in 6 new parishes, trained (business mgmt., gender & group dynamics, and collective mktg.) | Follow up training and support for newly trained farmer groups and their marketing associations | At least 20% of farmers in 10 parishes in Kamuli are involved in marketing > 100 kg. of beans each | 2015
| STEP 5 | FY 10 |  |  |  |  | Identify market information sources
|  | FY 11 |  |  |  |  | Plan for marketing | Assess marketing potential
|  | FY 12 | [8 empty] | Monitoring
4 | Vision of Impact pathway |  | New Methods of Consuming Beans (soups, porridge, extruded products, weaning foods, snacks) | 2012-08-31 | Volunteer Efforts for Development Concerns (NGO) & Food Processing Businesses | Community Farmers and Urban Consumers | Finalize extension materials for methods of bean processing (incl. cold extrusion) and cooking | Train 20 farmer groups in 4 current parishes on new methods of bean processing and cooking | Train 30 farmer groups in 6 new parishes new methods of bean processing and cooking | Work with 6 food processing businesses in develoment of marketing strategies for bean products | Obtain feedback from consumers (rural and urban) of new methods of consuming beans, adjust as appropriate | At least 15% of farmers in 10 parishes using alternative methods of preparing beans, consuming bean products, and complementary foods | 2015
| STEP 5 | FY 10 | [5 empty] | Assess current processing methods |  | Identify processors
|  | FY 11 |  |  |  |  | Identify distribution channels | Provide processing equipment |  |  | Monitoring of activities
FY 12

## PII-MSU-1
Impact Pathway Worksheet (Feel free to expand rows and columns as needed). Don't enter any thing in gray cells.
Name of your CRSP Project (Shorter version): |  |  |  |  | Combining Approaches to Improve Andean Beans
|  |  |  | Lead PI: | James D. Kelly
|  |  | STEP 1 |  | STEP 2 |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed |  |  |  |  | STEP 3
ID# |  |  | Project Outputs (expected by FY 12) | When to be achieved? | Next Users | Final Users | Step 4.1 | Step 4.2 | Step 4.3 | Step 4.4 | Step 4.5 | Vision of Success | Expected time to achieve the vision
1 | Vision of Impact pathway |  | 50 advanced lines in two growth habits and contrasting seed types with multiple disease resistance, consumer acceptance | 2010-04-01 | Farmers-CIAL members | Farmers- bean growers in country | On station seed increases | On farm testing and selection | On farm seed multiplication of selected lines | Basic seed available | Commercial seed available of new varieties | Successful release, adoption and utilization of at least four varieties - in two growth habit and four seed types for production in Rwanda and Ecuador | 2013
| STEP 5 | FY 10 |  |  |  |  | 100 kg seed produced | Testing and selection trials on 20 farms
|  | FY 11 | [5 empty] | Continue testing 25 lines on 20 farms | Multiplicationof seed of 25 lines - 75kg total
|  | FY 12 | [5 empty] | Continue testing 10 lines on 20 farms |  | 500kg of Basic seed produced for 10 lines total | 250kg commercial seed available for four new varieties
2 | Vision of Impact pathway |  | Increase knowledge for research scientists and stakeholders in bean production practices and constraints | 2012 | Research and outreach scientists and stakeholders | Government, Univesity, NGO Personel | Meeting with project leaders | Field days at CIALs, and on-station | Workshops, short courses | Radio, TV, internet, bulletins, and newspaper coverage | Country exchange of scientists and stakeholders
| STEP 5 | FY 10 |  |  |  |  | Country visit to discuss problems and needs - visit 20 CIALs 3 times per year | Ten field days - CIALs, 3 on station | 3 per year | estimated coverage in Ecuador, Europe and Rwanda - 10,000 persons
|  | FY 11 |  |  |  |  | Continue country visits | Ten field days - CIALs, 3 on station | 3 per year | estimated coverage in Ecuador, Europe and Rwanda - 10,000 persons
|  | FY 12 |  |  |  |  | Continue country visits | Ten field days - CIALs, 3 on station | 3 per year | estimated coverage in Ecuador, Europe and Rwanda - 10,000 persons | visit of Ecuadorian team to Rwanda
3 | Vision of Impact pathway
| STEP 5 | FY 10
FY 11
FY 12

## PII-MSU-2
Impact Pathway Worksheet (Feel free to expand rows and columns as needed). Don't enter any thing in gray cells.
Name of CRSP Project: |  |  |  |  | Expanding Pulse Supply & Demand in Africa & Latin America: Constraints & Opportunities
|  |  |  | Lead PI: | Rick Bernsten & Cynthia Donovan
|  |  | STEP 1 |  | STEP 2 |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed | [6 empty] | STEP 3
ID# |  |  | Project Outputs (expected by FY 12) | When to be achieved? | Next Users | Final Users | Step 4.1 | Step 4.2 | Step 4.2 | Step 4.3 | Step 4.4 | Step 4.5 | Step 4.6 | Vision of Success | Expected time to achieve the vision
1 | Mozambique: Vision of Impact pathway |  | Market price information on beans and cowpeas via cellphone, as well as through other means, will be available. Working with NGOs including World Vision and ADRA in Zambezia, targeting at least 4,000 farmers by 2012. | FY12 | Extension workers and farmers in the main bean production zones in Zambezia & Tete provinces (piloted with NGOs) | Bean/cowpea farmers and traders throughout the country | SIMA system designs info system for diffusion of bean/cowpea price info via SMS | SIMA Provincial systems incorporate info in local radio broadcasts as well as with SMS text | Local SIMAP partner with NGOs for system development and dissemination | Information to IIAM breeding staff and seed companies to ensure seed availability for beans/cowpeas with known marketable characteristics | Extension agents and lead farmers are trained in using SMS and in understanding market price info | Linakges established with local radio stations to broadcast market information | Traders are linked to the system and information to link traders and producers also disseminated through the system | At least 40% of farmers in the pilot zones (defined by NGO areas of work) accessing information to ensure profitability and motivate productivity enhancements and production increases | FY2014
| STEP 5 | FY 10 |  |  |  |  | SIMA system designs info system for diffusion of bean/cowpea price info via SMS | SIMA Provincial systems incorporate info in local radio broadcasts as well as with SMS text | Local SIMAP partner with NGOs for system development and dissemination
|  | FY 11 | [6 empty] | (Above cont) | Information to IIAM breeding staff and seed companies to ensure seed availability for beans/cowpeas with known marketable characteristics | Extension agents and lead farmers are trained in using SMS and in understanding market price info | Linakges established with local radio stations to broadcast market information
|  | FY 12 | [10 empty] | Traders are linked to the system and information to link traders and producers also disseminated through the system
2 | Angola: Vision of Impact pathway |  | Market price information will be circulated through cell phones. Farmers will access new markets for beans and cowpeas. Expected population affected would be at least 20% of World Vision's 27,000 farmers in the Planalto region. | Fy2012 | Extension workers and farmers in pilot areas | Traders and farmers in the key production zones | Marketing channels identified for beans in Planalto region | Farmer bean and cowpea marketing strategies identified and opportunities vealuated for improving marketing | Marketing channels identified for cowpeas in Planalto region | New markets evaluated for beans and cowpeas in Luanda | Extension agents and lead farmers for NGO are trained in market information use | All of NGO Farmer organizations in key bean production zone are linked to new marketing channels through cellphones and NGO |  | 50% of farmer associations working with NGO are marketing beans using new channels, where more profitable; 25% using price information | 2014
| STEP 5 | FY 10 |  |  |  |  | Marketing channels identified for beans in Planalto region | Farmer bean and cowpea marketing strategies identified and opportunities vealuated for improving marketing
|  | FY 11 | [6 empty] | Marketing channels identified for cowpeas in Planalto region | New markets evaluated for beans and cowpeas in Luanda | Extension agents and lead farmers for NGO are trained in market information use
|  | FY 12 | [9 empty] | All of NGO Farmer organizations in key bean production zone are linked to new marketing channels through cellphones and NGO
3 | Honduras: Vision of Impact pathway |  | A pilot bean production and marketing system for small-scale farmers oriented towards producing fair trade beans for export to a US retailer | FY 2011 | Small-scale farmers | US retailer of fair trade beans | Trial to assess organic bean production technologies | Assess costs for producing & exporting fairtrade beans | Identify a US retailer interested in purchasing fairtrade beans | Obtain third party fairtrade certification of the small-scale farmers | Finalize supply chain arrangements | Contract farmers to produce fair trade beans | Export fairtrade beans to a US retailer | Small-scale farmers produce and export fairtrade beans to th US | FY 2011
| STEP 5 | FY 10 |  |  |  |  | On-farm trials of organic bean production technologies | Identify all supply chain costs associated with exporting fair trade beans | Confirm interest of a US retailer to purchase fairtrade beans |  |  |  |  | Sixty farmers in the Yojora Lake region, who are members of the farmer association ASOCIALAYO (composed of 13 CIALS) will produce 20 mt of beans and export them to Whole Foods Inc as fairtrade beans. | FY11
|  | FY 11 | [5 empty] | Quantify all supply chain costs associated with exporting fair trade beans (e.g.,farmgate price, transport to export port, shipping to US, etc.) | Negotiate the purchase price that the US retailer will pay for fairtrade beans | Field visit to small scale farmers by a third party certifier (IMO or FLO), as required for fairtrade certification | Finalize supply chain arrangements (e.g., local exporter, US importer, US retailer) | Contract with farmers in the Yojora Lake region, who are members of the farmer association ASOCIALAYO, to produce 20 mt of beans | Export 20 mt of beans to Whole Foods Market
|  | FY 12 |  |  |  |  | NA-Project ends in FY 11 | NA-Project ends in FY 11 | NA-Project ends in FY 11 | NA-Project ends in FY 11 | NA-Project ends in FY 11 | NA-Project ends in FY 11 | NA-Project ends in FY 11

## PII-PSU-1
Impact Pathway Worksheet (Feel free to expand rows and columns as needed). Don't enter any thing in gray cells.
Name of your CRSP Project (Shorter version): |  |  |  |  | Material for J. Lynch on root traits as breeding tools
|  |  |  | Lead PI: | J Lynch
|  |  | STEP 1 |  | STEP 2 |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed
ID# |  |  | Project Outputs (expected by FY 12) | When to be achieved? | Next Users | Final Users | Step 4.1 | Step 4.2 | Step 4.3 | Step 4.4 | Step 4.5 | Step 4.6 | Vison of success | Expected time to achieve the vision
??? | Vision of Impact pathway |  | validated root traits used in bean breeding programs | some deployed now, others in the pipeline | bean breeders | Farmers in bean growing region | identify traits | confirm utility of traits for bean performance in stressful soils | characterize genetic control of traits | evaluate agroecological effects of traits on bean production systems | develop rapid screen for traits | work with breeders to use screen to identify promising sources and to assist introgression or recurrent selection for traits | Multiple varieties (5+) low-P bean seed available in local markets/ through seed-sharing networks. Bean income higher; local food supply more secure. | impacts are already being observed- extension of impacts dependent on adoption of bnoew bean seed by farmers- the subject of Dr. Findeis' activities
| STEP 5 | FY 10 |  |  |  |  | several traits have been identified- a new one may have been identified this year | ongoing in USA, South Africa, Mozambique | ongoing | ongoing | ongoing | ongoing
|  | FY 11 |  |  |  |  | ongoing- this is discovery research- impossible to predict | ongoing in USA, South Africa, Mozambique | ongoing | ongoing | ongoing | ongoing
|  | FY 12 |  |  |  |  | ongoing this is discovery research- impossible to predict | ongoing in USA, South Africa, Mozambique | ongoing | ongoing | ongoing | ongoing
SES | Vision of Impact pathway |  | SES assessment, policy studies | 2012 - first wave | IIAM field staff | Farmers in bean growing region, policy makers | Conduct ex ante impact assessment at SES experimental sites | Participatory Variety Selection at SES experimental sites | Test selected seed with randomly- selected farm households | Work with NGOs, comm. seed producers and extension to improve low-P seed distribution | Conduct ex post impact assessment at SES experimental sites | Provide policy makers with knowledge of documented impacts and constraints to low-P seed diffusion | Multiple varieties (5+) low-P bean seed available in local markets/ through seed-sharing networks. Bean income higher; local food supply more secure. Policy makers taking steps to improve bean seed system in Mozambique/region. | 1) 2012 - local impacts observaable in growing region; 2) 2015 - changes in national/national policy to reduce potential constraints to low-P seed diffusion
| STEP 5 | FY 10 |  |  |  |  | Complete baseline assessment, including analysis of seed sharing networks
|  | FY 11 | [5 empty] | Train IIAM staff in PVS/conduct PVS at selected SES experimental sites |  | Further develop networks with NGOs, comm. seed producers and extension in bean growing regions | Develop PVS and ex post survey instruments; pretest; train IIAM staff In use
|  | FY 12 | [5 empty] | Continue to conduct PVS at selected SES experimental sites | Test selected seed with randomly- selected farm households | Provide networks with materials (including information) necessary for low-P seed diffusion | Conduct ex post impact assessment at SES experimental sites | Work with IIAM staff to provide Mozambique policy makers with knowledge of documented impacts and constraints to low-P seed diffusion
Note on an ex post Impact pathway (Lynch, email 8-30-10)
here is what happened;
1) General concept of utility of root hairs for P acquisition was established in other crops over the 60s and 70s.
2) Early 1990s I showed with colleagues the magnitude of genetic variation for this trait in common bean.
3) Early 2000s we showed the substantial importance of such genetic variation for P acquisition in common bean, and identified QTL for breeding. Value of genetic variation for this trait and interaction with mycorrhizal colonization was confirmed in the field mid 2000s.
4) During all this time (ie 1987 through 2010) I emphasized the importance and value of this trait for bean breeding. Sources of this trait were used as parents in selection programs by CIAT in late 1990s, but no trait selection among progeny was employed. Juan Carlos Rosas learned of this work in the CRSP, and has begun more focused selection for root traits in his program, although I am not sure he is using root hairs per se as a selection criterion.
5) In mid 2000s I began training a bean breeder from Mozambique with support from the McKnight Foundation. In her PhD work she is specifically looking at introgression of this trait into adapted local material as a breeding tool. She plans to continue selection for this trait when she returns to her post at IIAM next year.
6) Impact in the field has been achieved through the use of long root hair parents in CIAT programs, but this is difficult to quantify as no direct trait selection occurred during line development. Direct trait selection is being conducted in IIAM; promising lines are in development; progress to farmer impact will be slow since cultivar certification is very slow in Mozambique, and formal seed dissemination mechanisms ineffective.
This well understood trait has substantial value for a primary yield limitation, but its use has been limited by the application of this tool by bean breeders, who have many competing priorities. Progress is now being achieved since I am training breeders directly. Potential impact is substantial once materials are delivered to farmers- the subject of Dr. Findeis' research.

## PII-UCR-1
Impact Pathway Worksheet (Feel free to expand rows and columns as needed). Don't enter any thing in gray cells.
Name of your CRSP Project (Shorter version): |  |  |  |  | Modern cowpea breeding
|  |  |  | Lead PI: | Philip Roberts
|  |  | STEP 1 |  | STEP 2 |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed |  |  |  |  | STEP 3
ID# |  |  | Project Outputs (expected by FY 12) | When to be achieved? | Next Users | Final Users | Step 4.1 | Step 4.2 | Step 4.3 | Step 4.4 | Step 4.5 | Vision of Success | Expected time to achieve the vision
1 | Vision of Impact pathway |  | Senegal advanced lines with large white grain and medium- to late maturity generated and available | 2012-09-01 | ISRA Seed Unit, Certified Seed Producers (NGOs, cops | Farmers | Multi-locational testing to validate results | Breeder seed production | Foundation seed | Production of 60 T of Certified (commercial) seed | Commercial seeds distributed available in market | At least 10% of farmers in the northern agro-ecological production zone in Senegal are growing the released variety | 2013
| STEP 5 | FY 10 |  |  |  |  | Multi-locational testing conducted in Senegal northern production region
|  | FY 11 |  |  |  |  | Multi-locational testing conducted in Senegal northern production region
|  | FY 12 | [5 empty] | 300 kg of Breeder seed per line produced by ISRA
2 | Vision of Impact pathway |  | Burkina Faso advanced lines with Striga resistance and improved grain quality (white) generated and available | 2010-09-12 | INERA Seed Unit, Certified Seed Producers (NGOs, cops | Farmers | Multi-locational testing to validate results | Breeder seed production | Foundation seed | Production of 60 T of Certified (commercial) seed | Commercial seeds distributed available in market | At least 10% of farmers in the central and northern agro-ecological zones in Burkina Faso are growing the released varieties | 2013
| STEP 5 | FY 10 |  |  |  |  | Multi-locational testing conducted in Burkina Faso central and northern production regions
|  | FY 11 |  |  |  |  | Multi-locational testing conducted in Burkina Faso central and northern production regions
|  | FY 12 | [5 empty] | 300 kg of Breeder seed per line produced by INERA
3 | Vision of Impact pathway |  | Extension of CRSP cowpea varieties from Burkina Faso and Senegal into Mali and Niger | 2010-09-12 | Mali and Niger NARS Seed Systems | Farmers in Mali and Niger | Multi-locational testing to validate results | Foundation seed | Foundation and Certified seed | Production of 30 T of Certified (commercial) seed | Commercial seeds distributed available in market | At least 5% of farmers in south-west Mali and western Niger are growing one of the released varieties (see note below) | 2014
| STEP 5 | FY 10 |  |  |  |  | Multi-locational testing conducted in Mali and Niger production regions
|  | FY 11 |  |  |  |  | Multi-locational testing conducted in Mali and Niger production regions
|  | FY 12 | [5 empty] | 2 T of Foundation seed produced by IER, Mali and INRAN, Niger
Note on # 3
On the points of clarification. The cowpeas being tested are Yacine and Melakh from ISRA, Senegal, and a series of new releases from INERA, Burkina Faso called KvX lines. These lines are all CRSP varieties. Melakh is popular in Senegal as is Yacine, with brown seed and good yield under dryer conditions and they both carry resistance to aphids, cowpea aphid-borne mosaic virus, and bacterial blight. The KVx lines are white-seeded, some with Striga resistance. I understand that all these countries have a formal release process, so we will be dealing with this for the one or two best performing lines for release in Mali and Niger.
Please add any of this into the worksheet as appropriate.

## PII-UIUC-1
Impact Pathway Worksheet (Feel free to expand rows and columns as needed). Don't enter any thing in gray cells.
Name of your CRSP Project (Shorter version): |  |  |  |  | Biological Foundations of Pest Management for Cowpeas in West Africa and Implementation of IPM-omics strategies
|  |  |  | Lead PI: | Barrry Robert Pittendrigh
|  |  | STEP 1 |  | STEP 2 |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed |  |  |  |  | STEP 3
ID# |  |  | Project Outputs (expected by FY 12) | When to be achieved? | Next Users | Final Users | Step 4.1 | Step 4.2 | Step 4.3 | Step 4.4 | Step 4.5 | Vision of Success | Expected time to achieve the vision
1 | Vision of Impact pathway |  | Pest control strategies for cowpea farmers and scaleable extension materials targeted for extension agents, NGOs, farmer organizations, and ultimately for cowpea farmers. | 2012-09-30 | NARS, IITA, over 100 extension agents in each of the host countries, 10 NGOs per country, and 100 Farmer groups per country | minimum of 1000 cowpea farmers per country. We will target to impact over 10,000 farmers in Niger and Burkina Faso either directly or indirectly through our extension materials. | Understand pest populations in host countries (using entomological and genomic tools). We will used both biology experiments in the field coupled with molecular markers to determine basic information about timing of major pests of cowpea and potential movement patterns). This data will be summarized in an online tracking system for future groups to add to this dataset for IPM management decisions both within the context of the project and beyond the current scope of the project. This will be completed by the end of the project in 2012. | Identify practical pest control strategies for given regions: (1) Insect-based biocontrol agents (a minimum of 2 released), (2) viral sprays, (3) host plant resistant strains, (4) cultural control practices (timing of plants and plant varieties that can escape insect attack), and (5) use of local plant products in spraying of crops to control pest insects (e.g., neem extracts). | Make available materials for pest control strategies: (1) Insect-based Biocontrol agents (a minimum of 2 bio-control agents will be released in Niger, Burkina Faso, and Benin), (2) viral sprays (one viral spray against Maruca will be tested in Benin, Burkina Faso, and Niger), (3) host plant resistant strains (a minimum of one strain will be released in Mali, Niger, Burkina Faso, and Nigeria), (4) cultural control practices (timing of plants and plant varieties that can escape insect attack -- this strategy will be promoted in Niger and Burkina Faso), and (5) use of local plant products in spraying of crops to control pest insects (e.g., neem extracts)(this strategy will be promoted in Niger, Burkina Faso, and Mali -- we expect that over 1000 farmers per country will be exposed to training material on this topic). These control strategies will be made available to a miniumum of over 100 extension agents in each of the host countries, 10 NGOs per country, and 100 Farmer groups per country. We expect to impact a minimum of 1000 farmers in each country and upwarrds of potentially 10,000 famers impated in NIger and Burkina Faso. | Identify partner organizations for large scale deployment of extension strategies: NARS programs (4 programs), local universities(>5 universities), NGOs (an average of 10 per country), and international instituations (IITA). We will take two approaches to this aspect of the project. The first will involve working with partner institutions directly in West Africa. The second will involve using e-mail as a strategy to contact NGOs and potential partner organizations where we can simply e-mail them cell phone videos that can be used for extension efforts in countries where cowpeas are grown and they have contact with cowpea farmers. We will also identify and work with partner organizations (a minimum of 5 organizations in West Africa) to build an online extension system that can be used beyond the scope of this project to continually deploy extension materials). | Deployment of pest control strategies. Biocontrol agents will primarily be deploed through IITA, INERA, and INRAN. We expect the biocontrol agents to establish in the field int he region where they have been deployed. We expect that by the end of the project, these biocontrol agents should have established in the fields and will reduce attack of their target species on cowpea by 50-70%. We will record for the population levels of these pest insects before and after release of the bio-control agents. We will also document reduced insect attack due to other control practices, including virally based control strategies, host plant resistant traits, and cultural practices. We will also use all our nextworks as described in Step 4.4 to deploy the extension materials we have developed associated with many of these above issues. The extension materials will include (1) a video on biocontrol agents, (2) animations on hermetic storage of cowpea, solar treating of cowpea, and neem spraying to control pests in the field. These animations will be deployed through cell phones and the voice overs will be translated into a minimum of six languages. Depending on the availability of resources we will create other animations dealing with pest control strategies for cowpea pests (hor plant resistance, cultural practices, and viral sprays), which can also be deployed through e-mail and ultimately onto cell phones. | Regional for ultimate large-scale use in host countries of pest control strategies. We will have a diversity of pest control strategies available to farmers for the control of insects that attack cowpeas. This will have been deployed by (1) the release of biocontrol agents, virally based sprays, neem based sprays, and host plant resistant trait, (2) use of farmer field schools and training sessions through NGO and farmer groups, and (3) through the deployment of cell phone animations/videos to explain well-established pest control strategies. The biocontrol agents will be released in Benin, Burkina Faso, and Niger. Additional potential releases may occur in Nigeria and Mali. In Burkina Faso, Mali, Nigeria, and Niger we expect in excess of 10,000 farmers will be exposed to the videos with changes in agricultural practices excess of 10,000 hectares. For the biocontrol agents we expect that in the piolot deployment regions we will be able to observe 20-30% increases in production due to decreased insect attack. We expect a total of over 10,000 hectares (across all countries) should have at least one biocontrol agent established in these areas. The envisioned output that will demonstrate that this project can be scaled up to do country-wide coverage of all of these strategies. | 2012
| STEP 5 | FY 10 |  |  |  |  | X | X |  | X | X
|  | FY 11 |  |  |  |  | X | X | X | X | X
|  | FY 12 |  |  |  |  | X |  | X | X | X
2 | Vision of Impact pathway |  | Development of extension materials and online extension sharing system that will be targeted at NARS scientists, extension agents, NGOs and farmer groups in order to increase the impact that these groups can have on deploying information into the hands of farmers. | 2012-09-30 | NARS, IITA, Extension Agents, NGOs, Farmer groups | Cowpea Farmers | Development of extension materials for low literate learners: these include a series of MP3 audio files, videos that can be played on cell phones (e.g., triple bagging, solar treating of cowpeas, neem spraying, and where time and resources permit other videso including safer ways to use traditional pesticides), posters, and booklets. | Development of online sharing system for extension materials. This is a system that will help us organize and freely share all the materials we have developed both for our project. This will allow us to organize materials in various languages and deployment strategies. We expect to have over 50 documents (which will include language variants) on this system by the end of 2011. | Testing of extension materials and feedback for improvements. This will occur through interactions between UIUC, host country scientists, and target organizations. Extension materials will be adapated or improved based on feeedback from these in country groups. | Identify partner organizations for large scale deployment of extension materials. These organizations will also be informed of our extension sharing system and the contents of this system for their own use. | Deployment of extension materials. This will be accomplished through a diversity of mechanisms as follows. Materials (CRSP created documents, animations, and videos) will be provided to NGOs and extension agenet for deployment. A total of 10 farmer field schools per country will have occurred in Niger, Burkina Faso, Nigeria, and Mali. Animations (a minimum of three different animations) will also be deployed through cell phones and Bluetooth technology through a minimum of 10 NGOs, 100 extension agents, local businesses supporting certain control strategies (e.g., triple bag manufacturers and distributors), and by e-mail to a minimum of 100 logical contact people per country. We will also have an online system supporting the exchange of extension materials. This system will allow us to track downloads of the materials. All organization will also be made aware and in some cases (NARS scientists, 20 technicians, extension agents and NGO) trained to use our online extension system. | Large scale use in host countries of extension materials for training farmers in pest control strategies. We expect that the cell phone animations will be easily transmitted through Bluetooth technology between extension agents and farmers. We also expect that our online extension sharing system will provide a useful base for a minimum of 500 cowpea educators (NARS scientists, technicians, extension educators, and NGOs) to access and share the extension materials we and others have developed. The videos will be released in Benin, Mali, Burkina Faso, Nigeria, and Niger. We expect in excess of 10,000 farmers will be exposed to the videos with changes in agricultural practices excess of 10,000 hectares. | 2012
| STEP 5 | FY 10 |  |  |  |  | X | X
|  | FY 11 | [5 empty] | X | X | X | X
|  | FY 12 | [7 empty] | X | X
3 | Vision of Impact pathway |  | Cross training of 5 NARS scientists (P.I.'s and co-P.I.'s), 20 technicians, and 10 NGOs/farmer organizations in traditional and electronic based extension programs | 2012-09-30 | 4 NARS programs, IITA, 100 extension agents, 10 NGOs, 100 farmer groups per country | A minimum of 1000 cowpea farmers impacted per country | Training of two host country scientist in development of extension materials and provide them with the necessary tools to continue to make and adapt many of these extension materials. | Cross training activities between host country scientists (6 scientists) and technicians (a minimum of 20 technicians). This will involve meetings bringing together most or all of the host country scientists [the first meeting occurred at the beginning of the project, several smaller meetings/workshops have already occurred (e.g., Niger in the summer of 2009) and one during the 2010 World Cowpea Congress]. A minimum of 20 technicians will be trained in various in country and between country cross-training activities (including within country workshops). On average we will interact with 10 NGOs per country to provide them with extension materials for deployment through their organizations. This will help to establish a network of people that can be called upon to deliver extension materials both within the project and beyond the scope of the current project. | Concepts and materials for low literate learners in the hands of farmers (a minimum of 1000 farmers per country). This will occur through farmer field schools, workshops, NGOs, farmer organization, and other conference/outreach activities. These end result outreach efforts will be based on materials and knowledge gained in steps 4.1 and 4.2. Contact information for all of these groups will be assembled such that future extension materials that are deployed can be easily distributed through these groups. |  |  | Development of a network of scientists, technicians, NGOs, and farmer organzations where extension materials can easily and continously be delivered beyond the scope of the current project. We expect to have 4 NARs and ITTA, as well as 100 extension agents and 10 NGOs/Farmer groups per country as part of this network for current and future deployment of extension materials. | 2012
| STEP 5 | FY 10 |  |  |  |  | X | X | X
|  | FY 11 | [5 empty] | X | X | X
|  | FY 12 | [5 empty] | X | X | X

## PII-UPR-1
Impact Pathway Worksheet (Feel free to expand rows and columns as needed). Don't enter any thing in gray cells.
Name of your CRSP Project (Shorter version): |  |  |  |  | PII-UPR-1
|  |  |  | Lead PI: | James Beaver
|  |  | STEP 1 |  | STEP 2 |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed |  |  |  |  | STEP 3
ID# |  |  | Project Outputs (expected by FY 12) | When to be achieved? | Next Users | Final Users | Step 4.1 | Step 4.2 | Step 4.3 | Step 4.4 | Step 4.5 | Vision of Success | Expected time to achieve the vision
1 | Vision of Impact pathway |  | Development, release and dissemination of improved bean cultivars for Central America, the Caribbean and Angola. | Sep-2012 | NARS breeders | Farm families | Selection and evaluation of bean breeding lines | Production of breeder seed by NARS | Production of foundation seed stocks by NARS, farmer associations and seed companies | Dissemination of foundation seed to bean producers |  | A significant number of farmers (100,000) in Central America and Haiti adopt improved bean varieties resulting in increased or more stable yields. Bean lines are identified as candidates for release in Angola. | September 2013
| STEP 5 | FY 10 |  |  |  |  | Multi-locational testing conducted in Central America, Haiti and Angola | Production of breeder seed by NARS
|  | FY 11 |  |  |  |  | " | " | Production of foundation seed stocks by NARS, farmer associations and seed companies | Dissemination of foundation seed to bean producers
|  | FY 12 |  |  |  |  | " | " | "
2 | Vision of Impact pathway |  | Selection of beans for adaptation to low N soils. | Sept 2013 | NARS breeders | Farm families | Selection and evaluation of bean breeding lines | Multi-locational testing conducted in Central America, Haiti and Angola | Release of improved bean germplasm and use as a parent by NARS breeding programs |  |  | Parental lines that can be used by NARS bean breeding programs to improve adaptation to low soil fertility | September 2013
| STEP 5 | FY 10 |  |  |  |  | Selection and evaluation of bean breeding lines
|  | FY 11 |  |  |  |  | " | Multi-locational testing conducted in Central America, Haiti and Angola
|  | FY 12 |  |  |  |  | " | " | Release of improved bean germplasm and use as a parent by NARS breeding programs
3 | Vision of Impact pathway |  | Develop and test molecular markers for disease and pest resistance. | Sept 2013 |  |  | Develop molecular markers for disease and pest resistance. | Test molecular markers to select for disease and pest resistance. |  |  |  | Molecular markers that can be used by NARS bean breeding programs to select bean lines with enhanced levels of disease and pest resistance | September 2013
| STEP 5 | FY 10 |  |  |  |  | Molecular marker development
|  | FY 11 |  |  |  |  | " | Testing of markers for disease and pest resistance.
|  | FY 12 | [5 empty] | "
4 | Vision of Impact pathway |  | Evaluation of other dry pulse crops for Central America and the Caribbean. | Sept 2013 | NARS breeders | Farm families | Selection and evaluation of bean breeding lines | Production of breeder seed by NARS |  |  |  | Release of Lima bean cultivars in in Haiti and Puerto Rico that is more productive or more resistant to diseases and pests than traditional varieties. | September 2013
| STEP 5 | FY 10 |  |  |  |  | Multi-locational testing conducted in Haiti and Puerto Rico
|  | FY 11 |  |  |  |  | " | Production of breeder seed by NARS
|  | FY 12 |  |  |  |  | " | "
5 | Vision of Impact pathway |  | Increase the capacity, effectiveness and sustainability of agriculture research institutions that serve the bean and cowpea sectors in Central America, Haiti and Angola. | Sept 2013 | NARS bean programs | NARS bean programs | Formal (M.S. degree) and informal training (workshop) activities |  |  |  |  | Trainees utilize knowledge to conduct new techniques or realize bean research activities with greater efficiency or effectiveness | Sept 2013
| STEP 5 | FY 10 |  |  |  |  | Training of HC personnel and informal training activities.
|  | FY 11 |  |  |  |  | Completion of M.S. training of HC personnel and informal training activities.
|  | FY 12 |  |  |  |  | "
Additional Notes regarding vision of success (J. Beaver, email 9-18-10):
Thanks for your message. With the additional funding from USAID, the goal is 100,000 farmers having access to the seed to test on their farm. Previous experience indicates that significant portion of the farmers will adopt the varieties. The establishment of sustainable, community-based seed production and dissemination systems should improve the rate of adoption of the varieties.
Concerning outputs 2 to 5, these are ongoing research and training activities. The full impact of these of these activities will not be achieved until the end and sometimes after the project has ended. For example, the development (by the Bean/Cowpea CRSP project), release and dissemination of DPC-40 in the Dominican Republic and Haiti.

## PIII-ISU-2
Impact Pathway Worksheet (Feel free to expand rows and columns as needed). Don't enter any thing in gray cells.
Name of your CRSP Project (Shorter version): |  |  |  |  | Biological Nitrogen Fixation (BNF)
|  |  |  | Lead PI: | Dr. Mark Westgate, ISU
|  |  | STEP 1 |  | STEP 2 |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed | [7 empty] | STEP 3
ID# | Program Activity |  | Project Outputs (expected by FY 12) | When to be achieved? | Next Users | Final Users | Step 4.1 | Step 4.2 | Step 4.3 | Step 4.4 | Step 4.5 | Step 4.6 | Step 4.7 | Step 4.8 | Vision of Success | Expected time to achieve the vision
1a | Evaluate effectiveness of stacked inoculant on local and improved germplasm |  | Quantitative relationships between local environmental conditions and genetic response to inoculants established | 2012-09-28 | Research stations and selected farmers | Small landholder Farmers | Identify local varieties and demonstration sites for field testing | Complete initial assessment of G x E, refine variety list | Confirm Trial I resuts, initiate on-farm trials | Test selected/advanced germplasm in zones with defined ecological limitations | Identify unique responses/limitations for improving seed yield across agro-ecological zones | Identify consistent response/limitations for improving seed yield across agro-ecological zones | Test optimum combinations of germplasm and inoculant for each ecological zone | Confirm optimum combinations of germplasm, inoculant, soil management for small - farm profitability | Best combinations of varieity and inoculants determined for 9 agro-ecological zones in Uganda, Rwanda, Tanzania | 2015
| STEP 5 | FY 10 |  |  |  |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.1: Obtain Seed for popular varieities; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.2: Establish Trial I in three agro-ecological zones in each country; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.3: Quantify yield of inoculant trial season 1
|  | FY 11 |  |  |  |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.2: Field trial 2 established on research stations and selected on-farm trials; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.3: Quantify yield advantage of inoculation for Fiield Trial II
|  | FY 12 |  |  |  |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.3: Field trial 3 established to confirm on-farm G x E; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.4: Quantify yield and economic advantage of inoculation in third season; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.5: Establish initial relationships between local agro-ecological conditions and G x E
2a | Identify parental materials for inheritance studies of BNF |  | Germplasm (for parental materials) with enhanced BNF identified | 2012-09-28 | Researchers | Breeders, IARCS | Select germplasm for evaluation with high and low BNF | Screen for BNF response to inoculants in US and HC | Test for BFN response to specific stresses | Advance positive response lines to field testing in US and HC. | Correlate reponse to inoculation in GH and field trials | Confirm G x E response for selected germplasm | Link G X E response to nodule occupancy/ efficiency | Relate BNF levels to rhizobia strains occupying nodules | Germplasm with superior nodulation characteristics identified and made available to breeding programs to improve BNF | 2012
| STEP 5 | FY 10 |  |  |  |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.1: Obtain experimental and adapted germplasm; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.2: Screen for increased BNF in low soil N +/- inoculants; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.3: Initiate Greenhouse BNF screenings
|  | FY 11 |  |  |  |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.2: Screen germplasm for BNF in low soil in HC field trials; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.3: Greenhouse trials initiated; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.4: Test parental lines for BNF in field
|  | FY 12 | [5 empty] | Complete screenings | Complete greenhouse trials | Complete parental line testing in the field | Confirmed correlative response of BNF in field and GH trials | Completed characterization of GXE for increased/stable BNF | Establish nodule rhizobia occupancy on selected lines | Confirm nodule rhizobia occupancy on selected lines
2b | Phenotype existing mapping populations for BNF response, populate with molecular markers, and conduct QTL analysis |  | Iinitial set of new QTLs for response to inoculation identified | 2012-09-28 | Researchers | Breeders, IARCS | Secure mapping populations for analysis | Establish field trials for phenotypic analysis | Correlate BFN response under field and controlled conditions | Advance RILs for SSR marker analysis | Conduct SSR marker analysis on selected lines | Complete initial analysis of potential new QTLs | Advance selected RILs to F3 for QTL analysis | Test selected RILs in agro-ecological zones to confirm QTLs for response to inoculation | QTLs for response to inoculation confirmed and employed in breeding programs to improve BNF | 2015
| STEP 5 | FY 10 |  |  |  |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.1: Increase seed of mapping populations for QTL analysis; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.2: Begin field testing of parental lines and selected populations
|  | FY 11 |  |  |  |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.2: Initiate phenotyping for divergent response of BNF; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.3: Establish correlative response of BNF in field and GH trials; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.4: Advance selected RILs to F2
|  | FY 12 |  |  |  |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.4: RIL populations phenotyped for BNF response; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.5: RIL populations populated with SSR markers
3c | Strengthen farmers' collective capabiliites to purchase inoculants and incorporate them into a profitable and sustainable system for fmall landholders |  | knowledge and recommendations generated from Inoculation trial results | 2012-09-28 | farmers | ag business concerns | Add inoculation information to PELUM agenda | Create appropriate information format for dissemination | Meet with key farmer groups in each HC | Share project results through PELUM network in HCs | Engage external funding agencies through HC ag stakeholders | Develop locally-relevant information materials for dissemination to PELUM network farmers | Develop extension training and farmer advocacy programs to promote access to inoculant technologies | Conduct PELUM meetings in all network countries | Fifteen (15) percent of farmers in all 12 SSA countries in PELUM network using innoculum technology | 2014
| STEP 5 | FY 10 |  |  |  |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.1: Incorporate BNF/inoculant information in PELUM activites
|  | FY 11 |  |  |  |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.2: Create training materials for distribution to PELUM farmers; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.3: Conduct advocacy meetings with farmer groups
|  | FY 12 |  |  |  |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.3: Conduct PELUM meetings in Rwanda, Uganda and Tanzania to present results of farmer profitability to 200+ partners; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.4: Incorporate research results into extension training programs, farmer advocacy and PELUM website in HCs; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.5: Determine potential for engaging international funding agencies to expand current technology transfer efforts
4 | Train students, field technicians, extensionists, and farmers on biological nitrogen fixation |  | Students, staff, farmers trained on ways to utilize, manage, and improve BNF | 2012-09-28 | staff, farmers | graduate students | identify beneficiaries | Identify beneficiaries of training programs | Train farmers and staff for research station and on-farm trials | Initiate graduate student research projects | Complete graduate student research projects | Develop scientific publications from graduate theses research | Graduate degrees awarded |  | All degree programs, internships, and visiting scientist activities successfully completed | 2012
| STEP 5 | FY 10 |  |  |  |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.1: Identify graduate and undergraduate students for research programs; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.2: Graduate and undergraduate students identified, enrolled; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.3: HC visiting scientist training completed
|  | FY 11 |  |  |  |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.2: Farmer cooperators identified; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.3: Farmer and staff training completed; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.4: Graduate student research projects underway
|  | FY 12 |  |  |  |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.5: Research results analyzed for review by BNF team; STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed Step 4.6: Reports, theses, and publications submitted to major professors

## PIII-MSU-3
Impact Pathway Worksheet (Feel free to expand rows and columns as needed). Don't enter any thing in gray cells.
Name of your CRSP Project (Shorter version): |  |  |  |  | PIII-MSU-3
|  |  |  | Lead PI: | Bennink
|  |  | STEP 1 |  | STEP 2 |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed |  |  |  |  | STEP 3
ID# |  |  | Project Outputs (expected by FY 12) | When to be achieved? | Next Users | Final Users | Step 4.1 | Step 4.2 | Step 4.3 | Step 4.4 | Step 4.5 | Vision of Success | Expected time to achieve the vision
1 | Vision of Impact pathway |  | Reduced inflammation | 2012 | other scientists and health advocates | individuals, food processors and retailers | Additional research related to pulse consumption and reduction in markers of chronic disease | consumer and commodity advocates instigate change in nutritional recommendations by national and international agencies | recommendations are implemented at grassroots | Changes in food choices | improved health and reduction in health costs | Reduction in chronic diseases | 2045
| STEP 5 | FY 10
FY 11
FY 12
2 | Vision of Impact pathway |  | Improved nutritional and immunological status | 2012 | other scientists and health advocates | individuals, food processors and retailers | Funding agencies are convinced to provide funds for large scale multi-national testing of nutritional intervention for PLHA | Decision makers are convinced that nutritional support is important enough to provide resources | policy change and commitment of resources for nutritional support and not just for drugs | changes in food choices and increased consumption of pulses and essential nutrients | improved health and reduction in health costs | Improved quality of life and decreased medical costs for people living with HIV and AIDS
| STEP 5 | FY 10
FY 11
FY 12
Note:
– The only thing that can be completed in the 30 mo timeframe is to achieve the outputs

## PIII-TAMU-1
Impact Pathway Worksheet (Feel free to expand rows and columns as needed). Don't enter any thing in gray cells.
Name of your CRSP Project (Shorter version): |  |  |  |  | TAMU P-III
|  |  |  | Lead PI: | Joseph Awika
|  |  | STEP 1 |  | STEP 2 |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed |  |  |  |  | STEP 3
ID# |  |  | Project Outputs (expected by FY 12) | When to be achieved? | Next Users | Final Users | Step 4.1 | Step 4.2 | Step 4.3 | Step 4.4 | Step 4.5 | Vision of Success | Expected time to achieve the vision
1 | Vision of Impact pathway |  | Identity and health promoting properties of cowpea bioactives | 2012-10-01 | Scientific community, nutritionists, Food scientists, NGOS, Policymakers | Farmers, nutritionists, Food manufacturers, Consumers | Establish effect of food processing on cowpea bioactives | Effect of feeding cowpea products on biomarkers in animal models | Short term human feeding trials | Long term human feeding trials | Community outreach targeting consumers, policymakers and farmers | 50% Increase in demand and use of cowpeas with enhanced health benefits in foods in HC; Improved health and food security among vulnerable groups; 30% Improvement in income for cowpea farmers | 2022
| STEP 5 | FY 10
|  | FY 11 |  |  |  |  | Select varieties with optimal bioactive properties | Identify suitable animal models
|  | FY 12 | [5 empty] | Identify processes that would optimize retention of bioactivity in cowpea | identify target populations and biochemical outcomes |  | Share preliminary data with stakeholders
2 | Vision of Impact pathway |  | Identity of healthy cowpea lines and and heritability of health promoting traits in cowpea | 2012-10-01 | HC breeders, Food Scientists, Nutritionists, Policymakers, scientific community | Seed companies, Farmers, Breeders, Policymakers, Food manufacturers | Infuse bioactivity traits in cowpea lines with suitable agronomic properties | Field adaptability trials across different environmets | Development of suitable local varieties by HC breeders and seed companies | Farmer training and field demonstrations | Community outreach targeting policymakers and farmers | Development of at least 2 local varieties with high phytochemical content and enhanced health benefits in each HC | 2017
| STEP 5 | FY 10
|  | FY 11 |  |  |  |  | Perform relevant crosses using parents with desirable agronomic traits |  |  | Stakeholder workshop with policymakers and farmer organization representatives
|  | FY 12 |  |  |  |  | Perform relevant crosses using parents with desirable agronomic traits | Field trials at TAMU and Zambia | HC breeders select suitable local varieties for improvement | Stakeholder workshop with policymakers and farmer organization representatives | Share findings with scientists and HC stakeholders to encourage adoption of specific phenotypes
3 | Vision of Impact pathway
| STEP 5 | FY 10
FY 11
FY 12
3 | Vision of Impact pathway
| STEP 5 | FY 10
FY 11
FY 12
4 | Vision of Impact pathway
| STEP 5 | FY 10
FY 11
FY 12

## PIII-KSU-1
Impact Pathway Worksheet (Feel free to expand rows and columns as needed). Don't enter any thing in gray cells.
Name of your CRSP Project (Shorter version): |  |  |  |  | Pulse Value Chain Initiative
|  |  |  | Lead PI: | Vincent Amanor-Boadu
|  |  | STEP 1 |  | STEP 2 |  | STEP 4: Program Logic (identify steps to reach next users and final users to achieve the vision of success) add columns if needed |  |  |  |  | STEP 3
ID# |  |  | Project Outputs (expected by FY 12) | When to be achieved? | Next Users | Final Users | Step 4.1 | Step 4.2 | Step 4.3 | Step 4.4 | Step 4.5 | Vision of Success | Expected time to achieve the vision
1 | Vision of Impact pathway |  | Information and knowledge about the structure, conduct and performance in bean and cowpea supply chains in Zambia | 2012 | Producers and their downstream partners | Policy makers and producers and their downstream partners | Establish baseline knowledge about structure, conduct and performance in the bean and cowpea supply chains through primary data collection and analysis | Explore effect of current institutional structures and policies on baseline conditions through engaged conversations and simulations with policymakers | Develop and test alternative governance systems that minimize policy impacts and enhance participation | Use information from tests to improve governance system alternatives and develop |  | Effective participation by the majority of producers in bean and cowpea supply chains as a result of improved understanding of value chain operations, leading to higher value accretion and resulting in improved household food and nutrition security. Realisitic quantitative metrics will be supplied after preliminary field work is completed in Feb. 2011. | 2015
| STEP 5 | FY 10
|  | FY 11 |  |  |  |  | Establish baseline knowledge about structure, conduct and performance in the bean and cowpea supply chains through primary data collection and analysis | Explore effect of current institutional structures and policies on baseline conditions through engaged conversations and simulations with policymakers
|  | FY 12 | [6 empty] | Develop and test alternative governance systems that minimize policy impacts and enhance participation | Use information from tests to improve governance system alternatives and develop
2 | Vision of Impact pathway |  | Development of adoption protocols to enhance the relationship between value accretion and gender | 2011 | Producers | Producers and policy makers | Establish current participation and value accretion situation by gender | Engage female producers to explicitly explore challenges and opportunities for effective participation in supply chains | Explore opportunities to implement ideas emanating from the engagements with female producers | Discuss simulation results with producers and develop clear feasible implementation and/or adoption protocols | Engage government and other organizations to implement ideas that prove promising after simulations and testing | Enhanced income accruing to female producers through effective engagement in their supply chains. Realisitic quantitative metrics will be supplied after preliminary field work is completed in Feb. 2011 | 2015
| STEP 5 | FY 10
|  | FY 11 |  |  |  |  | Establish current participation and value accretion situation by gender
|  | FY 12 | [5 empty] | Engage female producers to explicitly explore challenges and opportunities for effective participation in supply chains | Explore opportunities to implement ideas emanating from the engagements with female producers and simulate ideas for effects on expected outcome | Discuss simulation results with producers and develop clear feasible implementation and/or adoption protocols | Engage government and other organizations to help implement ideas that prove promising after simulations and testing
3 | Vision of Impact pathway
| STEP 5 | FY 10
FY 11
FY 12